SUPPORTPILOT

Master Action Plan

Workstreams, phases, milestones, ownership, and dependencies for delivery

| Document ID | SP-PLAN-001 |
| --- | --- |
| Status | Execution plan derived from the architecture baseline |
| Version | 1.0 |
| Date | 2026-09-07 |
| Baseline documents | SP-PRD-001, SP-ARCH-001, SP-DATA-001, SP-BUILD-001, SP-OPS-001 |
| Companion documents | SP-PLAN-002 backlog, SP-PLAN-003 runbook, SP-PLAN-004 tests, SP-PLAN-005 registers |

# Purpose

This document turns the agreed SupportPilot design baseline (SP-PRD-001, SP-ARCH-001, SP-DATA-001, SP-BUILD-001, SP-OPS-001) into an executable plan. It defines workstreams, phases, milestones, ownership, dependencies, and the gate that each phase must pass before the next phase starts. It adds no new product scope and changes no security decision.

# Contents

How to Use This Plan

Planning Assumptions

Workstreams

Phase Plan

Milestone Schedule

Critical Path and Dependencies

Ownership and RACI

Team and Capacity

Working Cadence

Phase Gate Procedure

Status Reporting

Escalation and Replanning

Plan Risks to Watch

# 1. How to Use This Plan

This plan is the delivery view of the baseline. Each phase produces a working vertical slice that keeps the final identity, authorization, database, approval, and audit boundaries in place. Read this document for sequence and ownership, SP-PLAN-002 for the task list, SP-PLAN-003 for the exact build steps, SP-PLAN-004 for the tests that close a phase, and SP-PLAN-005 for the open decisions and risks that can stop progress.

Planning rule: A phase is complete only when its positive and negative authorization tests pass and its evidence is stored. A working chat response is never a completion signal.

# 2. Planning Assumptions

| ID | Assumption | Effect if wrong |
| --- | --- | --- |
| AP-01 | Week 1 begins Monday 2026-09-07 and a week is five working days. | All milestone dates shift by the same amount. |
| AP-02 | One delivery team works on SupportPilot with the roles listed in section 8. | Phases 2 and 4 extend first because they carry the most parallel work. |
| AP-03 | Onyx, Keycloak, OPA, and PostgreSQL run locally under Docker Compose for phases 0 to 4. | Phase 0 grows and phase 1 starts later. |
| AP-04 | A model provider account and quota for Onyx are available in week 1. | Phase 1 read flow cannot be demonstrated end to end on time. |
| AP-05 | Refund execution in phases 4 and 5 uses a provider sandbox, not a live financial system. | Phase 4 needs a formal risk acceptance and a separate approval. |
| AP-06 | A security reviewer is available for each phase gate and for control-plane changes. | Gates queue and the launch gate moves. |
| AP-07 | The open decisions in SP-PLAN-005 are answered by the phase noted there. | The affected workstream stops at its decision point. |
| AP-08 | Weeks 16 and 17 contain public holidays; no gate is scheduled inside a change freeze. | Phase 5 finishes later than the dates in section 5. |

# 3. Workstreams

Work is organized into nine workstreams. A workstream owns a boundary from the architecture, not a phase. Every task in SP-PLAN-002 belongs to exactly one workstream.

| ID | Workstream | Owns | Baseline reference |
| --- | --- | --- | --- |
| WS-A | Platform and environment | Repository, container images, networks, secret mounts, health checks, local bootstrap. | SP-BUILD-001 sections 2 and 3 |
| WS-B | Identity | Keycloak realm, clients, users, groups, MFA, token verification middleware. | SP-DATA-001 sections 1 and 2 |
| WS-C | Authorization policy | OPA bundle, policy input contract, reason codes, policy tests, publication path. | SP-DATA-001 sections 3 and 4 |
| WS-D | Data and database | Schema, roles, grants, RLS, migrations, seeds, database tests. | SP-DATA-001 sections 5 to 8 |
| WS-E | API and tools | Tool endpoints, schemas, resource lookup, response minimization, audit writes. | SP-ARCH-001 section 3 |
| WS-F | Agent integration | OpenAPI action document, Onyx action and agent configuration, loop and cost budgets. | SP-BUILD-001 section 7 |
| WS-G | Actions, approval, worker | Action state machine, approval portal, worker, adapters, idempotency, reconciliation. | SP-ARCH-001 section 7 |
| WS-H | Security verification | Test matrix, agent abuse cases, tenant isolation suite, evidence capture. | SP-OPS-001 sections 3 to 6 |
| WS-I | Operations and release | Pipeline, monitoring, runbooks, backup and restore, change control, gate evidence. | SP-OPS-001 sections 7 to 12 |

# 4. Phase Plan

Phases follow the build plan in SP-BUILD-001 section 4. Entry criteria protect a phase from starting on an unproven foundation. Exit criteria are evidence, not opinion.

| Phase | Name | Weeks | Lead workstreams | Entry criteria | Main deliverables | Exit evidence |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 0 | Project baseline | W01-W02 | WS-A | Approved baseline documents and access to source control, container registry, and model provider. | Repository structure, pinned images, separated networks, excluded local secret files, one bootstrap command, one verify command, health checks. | Environment starts and verifies from a clean machine. |
| Phase 1 | Identity and one protected read | W03-W05 | WS-B, WS-C, WS-D, WS-E, WS-F | Phase 0 exit passed. Keycloak realm design and get_order schema reviewed. | Realm and clients, individual OAuth forwarding from Onyx, token verification, get_order endpoint, first OPA rule and tests, core tables with RLS, seeded organizations. | T-001 to T-007 pass end to end, including cross-tenant denial at API and database layers. |
| Phase 2 | Complete read capabilities | W06-W08 | WS-E, WS-C, WS-D, WS-F, WS-H | Phase 1 exit passed. Field-level response schemas reviewed. | search_customers, get_customer, get_ticket, order items, shipment status, pagination, field filtering, audit events for allowed and denied calls, agent budgets. | T-008 and T-014 pass; instructions stored in ticket data change neither authorization nor tool availability. |
| Phase 3 | Controlled low-impact writes | W09-W10 | WS-E, WS-D, WS-C | Phase 2 exit passed. Note content and length constraints agreed. | add_internal_note with server-derived author, ownership and visibility policies, concurrency protection, write audit evidence. | Write path tests pass, including stale-state rejection and cross-tenant write denial. |
| Phase 4 | Approval and worker | W11-W14 | WS-G, WS-C, WS-D, WS-E, WS-H | Phase 3 exit passed. Approval rule, separation-of-duty rule, and provider sandbox confirmed. | Action request, decision, job, execution and idempotency tables; propose_refund and get_action_status; approval portal; worker with lease, payload hash check, retries, reconciliation. | T-009 to T-013 pass; no protected effect before approval and no effect executed twice. |
| Phase 5 | Hardening and operational readiness | W15-W18 | WS-I, WS-A, WS-H | Phase 4 exit passed. Production platform and secret manager selected. | Production secret handling, centralized logs, metrics, traces, alerts, backups and restoration test, pipeline scans, security assessments, load, failure, recovery and rollback tests. | All launch gate rows in SP-PLAN-005 are pass or formally accepted with an owner and a date. |

# 5. Milestone Schedule

Dates assume AP-01. Every milestone is a gate review with named evidence, not a status meeting.

| ID | Milestone | Target | Pass condition |
| --- | --- | --- | --- |
| M0 | Environment baseline accepted | Fri 2026-09-18 | A clean machine reaches a verified running environment with one command. |
| M1 | First protected read proven | Fri 2026-10-09 | Alice reads a Cedar order; the same request for another organization returns no protected data. |
| M2 | Read surface complete | Fri 2026-10-30 | All read tools return minimized fields with pagination, audit events, and passing injection tests. |
| M3 | Controlled write proven | Fri 2026-11-13 | Internal notes are created with server-derived authorship and full audit evidence. |
| M4 | Approval and execution proven | Fri 2026-12-11 | Refund proposal, independent approval, single execution, and reconciliation evidence exist. |
| M5 | Operational readiness complete | Fri 2027-01-08 | Monitoring, runbooks, restore test, pipeline scans, and security assessment results are in place. |
| M6 | Launch gate decision | Fri 2027-01-15 | Every gate row in SP-PLAN-005 section 4 is pass or accepted risk with owner and expiry. |

Freeze note: Weeks 16 and 17 include public holidays and a change freeze. No gate, migration, or policy publication is scheduled inside the freeze; M5 evidence is prepared before it and reviewed after it.

# 6. Critical Path and Dependencies

The critical path runs through identity, then policy and database, then the action machinery. Delay on any of these moves the launch gate one week for one week.

| Step | Depends on | Why the order cannot change |
| --- | --- | --- |
| Keycloak realm and clients | Phase 0 networks and compose baseline | Token verification cannot be tested without a running issuer. |
| API token verification | Keycloak realm and clients | Every later authorization decision needs a verified subject. |
| Trusted resource lookup | Core schema and seed data | Policy input must contain server-side resource attributes, not model arguments. |
| OPA decision call | Token verification and resource lookup | Policy input is built only from verified identity and trusted resource data. |
| RLS policies and runtime roles | Migration role separation | Runtime roles must not own protected tables, so ownership is set at migration time. |
| Read tools | OPA decision call and RLS | A tool must not exist before both authorization layers apply to it. |
| Onyx action registration | Read tools and OpenAPI document | The model may call only operations that already enforce authorization. |
| Audit events | Read and write tools | Evidence is written where trusted decisions and effects occur. |
| Action state machine | Audit events and write path | State transitions must be recorded transactionally with evidence. |
| Approval portal | Action state machine | Approval binds to an immutable stored payload hash. |
| Worker execution | Approval portal and idempotency tables | Execution requires a valid approval and a reservation that prevents duplication. |
| Operational readiness | All execution paths | Monitoring, runbooks, and restore tests must cover the finished behavior. |

# 7. Ownership and RACI

Roles are delivery roles. Replace each role with a named person before the plan is baselined; an unnamed owner is tracked as an open item in SP-PLAN-005.

| Workstream | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| WS-A Platform | Platform engineer | Engineering lead | Security engineer | Product owner |
| WS-B Identity | Identity engineer | Security lead | Platform engineer, Onyx owner | Product owner |
| WS-C Policy | Policy engineer | Security lead | Backend engineer, Product owner | Auditor |
| WS-D Database | Database engineer | Engineering lead | Security engineer | Operations |
| WS-E API and tools | Backend engineer | Engineering lead | Policy engineer, Product owner | Onyx owner |
| WS-F Agent integration | Onyx owner | Product owner | Backend engineer, Security engineer | Support managers |
| WS-G Actions and worker | Backend engineer | Engineering lead | Finance approver, Security lead | Operations |
| WS-H Verification | Security engineer | Security lead | All engineers | Product owner, Auditor |
| WS-I Operations | Operations engineer | Operations lead | Security lead, Engineering lead | All stakeholders |

# 8. Team and Capacity

| Role | Phases with heaviest load | Notes |
| --- | --- | --- |
| Engineering lead | All | Owns sequencing, gate readiness, and cross-workstream conflicts. |
| Backend engineer (API) | 1, 2, 3, 4 | Tool endpoints, resource lookup, action state machine, worker. |
| Database engineer | 1, 3, 4 | Schema, roles, grants, RLS policies, migration job, database tests. |
| Identity engineer | 1, 5 | Realm, clients, MFA policy, key rotation, service identities. |
| Policy engineer | 1, 2, 4 | OPA rules, obligations, reason codes, policy test suite. |
| Onyx owner | 1, 2, 4 | Action registration, agent instructions, budgets, tool descriptions. |
| Security engineer | All | Threat model upkeep, abuse cases, injection corpus, review of every gate. |
| Operations engineer | 0, 5 | Pipeline, monitoring, backup and restore, runbooks, release evidence. |
| Product owner | 0, 2, 4, 5 | Scope, prohibited actions, approval rules, launch decision. |

# 9. Working Cadence

Daily: short delivery sync focused on blocked tasks and gate risk, not status narration.

Weekly: security review of new tools, schemas, policies, and prompts before they are merged.

Weekly: backlog grooming against SP-PLAN-002; a task without exit evidence is not accepted as ready.

Per phase: gate review with the evidence package described in section 10.

Per control-plane change: review as defined in SP-OPS-001 section 10, regardless of phase.

Monthly: risk register review in SP-PLAN-005, including expiry of accepted risks.

# 10. Phase Gate Procedure

The workstream leads confirm that every task for the phase in SP-PLAN-002 is closed or formally deferred.

The test owner runs the phase test set from SP-PLAN-004 and attaches results, including negative cases.

The security engineer confirms threat-model updates and that no new authority was granted to the model or to a runtime service.

The database engineer confirms grants, RLS behavior, and the migration version for the phase.

The evidence package is stored with source revision, image digests, policy version, and schema version.

The engineering lead and security lead record a pass, a conditional pass with owner and date, or a fail.

A conditional pass creates a tracked item in SP-PLAN-005 with an expiry date. Silent deferral is not allowed.

# 11. Status Reporting

| Report | Frequency | Content |
| --- | --- | --- |
| Delivery status | Weekly | Phase progress, blocked tasks, decision requests, milestone confidence. |
| Security status | Weekly | New or changed tools, policies, prompts; open findings; injection test results. |
| Gate report | Per phase | Evidence package, test results, accepted conditions with owners and dates. |
| Risk report | Monthly | Register changes, new risks, expired acceptances, mitigation progress. |
| Launch readiness | Phase 5 | Gate tracker state, remaining conditions, rollback and monitoring confirmation. |

# 12. Escalation and Replanning

| Trigger | Action | Decision owner |
| --- | --- | --- |
| A phase exit test fails twice on the same control | Stop new feature work in that workstream; fix the control and add a regression test. | Security lead |
| An open decision in SP-PLAN-005 passes its needed-by phase | Apply the recorded default or stop the dependent workstream; do not improvise a substitute. | Product owner |
| A milestone slips more than one week | Rebaseline the following milestones; never compress a security phase to recover time. | Engineering lead |
| A control-plane boundary would need to be weakened to meet a date | Reject the change and escalate; the boundary is baseline, not schedule scope. | Security lead |
| The provider sandbox is unavailable for phase 4 | Continue with the fake adapter and record provider evidence as an open launch-gate condition. | Product owner |

# 13. Plan Risks to Watch

These risks are tracked in full in SP-PLAN-005. They are repeated here because they most often move the launch date.

Identity integration between Onyx and Keycloak takes longer than planned and blocks the whole critical path.

Row-level security work starts after the application queries exist, which invites a table-ownership mistake.

Agent abuse testing is treated as a phase 5 activity instead of a per-phase activity.

Approval and worker work is compressed because it arrives late in the schedule.

Open decisions on the system of record and the financial integration remain unanswered into phase 4.