SUPPORTPILOT

Work Breakdown and Task Backlog

Every delivery task with owner, dependency, and closing evidence

| Document ID | SP-PLAN-002 |
| --- | --- |
| Status | Execution plan derived from the architecture baseline |
| Version | 1.0 |
| Date | 2026-09-07 |
| Parent document | SP-PLAN-001 Master Action Plan |
| Task count | 99 tasks across phases 0 to 5, plus 8 standing tasks |

# Purpose

This document lists every task required to deliver SupportPilot, phase by phase. Each task has an identifier, a workstream, a dependency, and the evidence that closes it. It is the working backlog behind SP-PLAN-001 and the source for sprint planning and gate reviews.

# Contents

How to Read the Backlog

Phase 0 Tasks

Phase 1 Tasks

Phase 2 Tasks

Phase 3 Tasks

Phase 4 Tasks

Phase 5 Tasks

Cross-Phase Standing Tasks

Definition of Ready

Definition of Done

# 1. How to Read the Backlog

Task identifiers use the pattern P<phase>-<number>. The workstream column uses the identifiers from SP-PLAN-001 section 3. The size column is a relative estimate: S is up to one day, M is two to three days, L is four days or more and should be split if it cannot be finished inside one week. The evidence column states what must exist for the task to be closed; a demonstration without evidence does not close a task.

Backlog rule: No task may add a tool, a database grant, a policy rule, or an outbound destination that is not already described in the baseline documents. Such a change is a control-plane change and follows SP-OPS-001 section 10 first.

# 2. Phase 0 Tasks

Goal: a clean machine reaches a verified running environment with one command, with the final network and secret boundaries already in place.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P0-01 | Create the repository structure from SP-BUILD-001 section 2 with README and code owners. | WS-A | S | - | Repository tree matches the baseline layout. |
| P0-02 | Record coding standards, review rules, and branch protection for policy, schema, and tool changes. | WS-A | S | P0-01 | Protected branches configured and documented. |
| P0-03 | Copy the threat model into docs/architecture and open the decision record folder. | WS-H | S | P0-01 | Threat model and first decision records committed. |
| P0-04 | Pin container image digests and dependency versions for every service. | WS-A | M | P0-01 | Lock files and pinned digests committed; no floating tags. |
| P0-05 | Create separate Docker networks for edge, application, policy, and database traffic. | WS-A | M | P0-04 | Compose shows four networks; PostgreSQL and OPA are unreachable from the edge network. |
| P0-06 | Define compose services for Onyx, Keycloak, API, OPA, PostgreSQL, worker, approval portal, migration job. | WS-A | L | P0-05 | All services start; the migration job runs once and exits. |
| P0-07 | Create local secret files with file mounts and add them to version-control exclusions. | WS-A | M | P0-06 | No secret value in the repository; each service mounts only its own secret. |
| P0-08 | Write .env.example with names and safe defaults only. | WS-A | S | P0-07 | Example file contains no real credential. |
| P0-09 | Add health checks and readiness dependencies to every service. | WS-A | M | P0-06 | Environment reports healthy without manual retries. |
| P0-10 | Write bootstrap-local.ps1 and verify-local.ps1. | WS-A | M | P0-09 | One command starts the environment; one command reports pass or fail per check. |
| P0-11 | Add a secret-scanning and formatting pre-commit or pipeline stage. | WS-I | S | P0-02 | A committed test secret is blocked by the scan. |
| P0-12 | Run the phase 0 gate review. | WS-A | S | P0-10, P0-11 | Signed gate record for milestone M0. |

# 3. Phase 1 Tasks

Goal: an authenticated user reads one authorized order end to end, and the same request for another organization is denied at both the API and the database.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P1-01 | Create the Keycloak realm, clients, redirect addresses, groups, and roles. | WS-B | M | P0-12 | Realm export committed; login works for a seeded user. |
| P1-02 | Create test users and memberships: agent, manager, finance approver, auditor, and a second-organization agent. | WS-B | S | P1-01 | Each user signs in and receives the expected roles. |
| P1-03 | Enable the required multi-factor policy for the local realm. | WS-B | S | P1-01 | Login requires the configured second factor. |
| P1-04 | Configure Onyx authentication and individual OAuth forwarding for the SupportPilot action. | WS-F | L | P1-01 | The API receives a user-bound token, not a service token. |
| P1-05 | Build token verification middleware: issuer, audience, signature, algorithm, expiry, not-before, key cache. | WS-B | L | P1-01 | Negative token tests all reject before any policy or database access. |
| P1-06 | Write the migration for organizations, users, memberships, customers, orders. | WS-D | M | P0-12 | Migration applies and rolls forward cleanly on an empty database. |
| P1-07 | Create sp_migrator_role, sp_api_role, sp_worker_role, sp_auditor_role with least-privilege grants. | WS-D | M | P1-06 | Runtime roles have no ownership, no BYPASSRLS, and no schema privileges. |
| P1-08 | Enable and force row-level security on the phase 1 tables and add tenant policies. | WS-D | M | P1-07 | Policy tests show zero rows when request context is missing. |
| P1-09 | Implement transaction-local request context (SET LOCAL user and organization). | WS-D | M | P1-08 | Pooled-connection test shows no context leaking to the next request. |
| P1-10 | Seed two organizations, users, customers, and orders including ORD-2001. | WS-D | S | P1-08 | Seed script is repeatable and produces known test data. |
| P1-11 | Build the trusted resource lookup that loads order attributes before policy evaluation. | WS-E | M | P1-09 | Policy input contains server-side attributes only. |
| P1-12 | Implement the OPA client with a short timeout and deny on unavailable, undefined, or malformed responses. | WS-C | M | P1-05 | Stopping OPA denies the protected call with a controlled error. |
| P1-13 | Write the first OPA rule for order.read with default deny, reason code, and policy version. | WS-C | M | P1-12 | Policy unit tests pass for allow and deny cases. |
| P1-14 | Build the get_order endpoint with a strict path pattern and a bounded response schema. | WS-E | M | P1-11, P1-13 | Malformed identifiers are rejected by schema before any lookup. |
| P1-15 | Publish the OpenAPI 3.1 action document containing only get_order. | WS-F | S | P1-14 | Document validates and lists exactly one operation. |
| P1-16 | Register the action in Onyx and set agent instructions for tool use and error handling. | WS-F | M | P1-15, P1-04 | The model can call get_order and nothing else. |
| P1-17 | Add correlation identifiers across Onyx, API, OPA, and database calls. | WS-E | S | P1-14 | One request can be reconstructed from logs across services. |
| P1-18 | Write the first audit event for an allowed and a denied order read. | WS-E | M | P1-14 | Audit rows contain actor, action, resource, decision, policy version, request id. |
| P1-19 | Run test cases T-001 to T-007 and store results. | WS-H | M | P1-16, P1-18 | All seven cases pass with stored evidence. |
| P1-20 | Run the phase 1 gate review. | WS-B | S | P1-19 | Signed gate record for milestone M1. |

# 4. Phase 2 Tasks

Goal: the full read surface exists with minimized responses, pagination, audit coverage, and proven resistance to instructions stored in business data.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P2-01 | Extend the schema with order items, shipments, tickets, ticket messages, internal notes. | WS-D | M | P1-20 | Migration applied with organization columns on every protected table. |
| P2-02 | Add RLS policies and role grants for every new table. | WS-D | M | P2-01 | Every new table has a tested policy for each runtime role. |
| P2-03 | Build search_customers with mandatory pagination and a maximum result size. | WS-E | L | P2-02 | Result size and page limits are enforced server side. |
| P2-04 | Build get_customer with an approved field subset. | WS-E | M | P2-02 | Response schema excludes sensitive fields by construction. |
| P2-05 | Build get_ticket with permitted conversation history and visibility rules. | WS-E | L | P2-02 | Restricted messages never appear for an unauthorized role. |
| P2-06 | Extend get_order with items and shipment status under the same authorization path. | WS-E | M | P2-02 | Joined data respects tenant policy at the database layer. |
| P2-07 | Add OPA rules and tests for customer.read, ticket.read, and field obligations. | WS-C | L | P2-03 | Obligations return allowed fields and the API applies them. |
| P2-08 | Implement obligation handling so denied fields are removed before the response is built. | WS-E | M | P2-07 | A field removed by policy is absent from the response and from logs. |
| P2-09 | Add sorting allowlists, query timeouts, and maximum row limits to all read repositories. | WS-D | M | P2-03 | Unlisted sort fields are rejected; long queries are cut off safely. |
| P2-10 | Add audit events for every allowed and denied tool call with stable reason codes. | WS-E | M | P2-06 | Audit coverage test shows an event for each tool and each outcome. |
| P2-11 | Extend the OpenAPI document with the new operations and bounded response schemas. | WS-F | M | P2-06 | No operation returns an open object or an unbounded array. |
| P2-12 | Configure model-call, tool-call, time, token, and cost budgets for the agent. | WS-F | M | P2-11 | Exceeding the budget stops the loop with a controlled message. |
| P2-13 | Seed prompt-injection records into ticket messages, customer names, and order notes. | WS-H | M | P2-05 | Injection corpus is versioned and reusable in every later phase. |
| P2-14 | Build the agent abuse test suite: direct injection, indirect injection, tool confusion, argument manipulation. | WS-H | L | P2-13 | Suite runs on demand and reports per-case results. |
| P2-15 | Add exfiltration and memory-isolation tests across two users and two organizations. | WS-H | M | P2-14 | No cross-session or cross-tenant content appears in any response. |
| P2-16 | Add response and log redaction checks for secrets and excessive fields. | WS-H | M | P2-10 | Redaction test scans responses, logs, and traces. |
| P2-17 | Run test cases T-008 and T-014 and the abuse suite; store results. | WS-H | M | P2-14, P2-12 | All cases pass with stored evidence. |
| P2-18 | Run the phase 2 gate review. | WS-E | S | P2-17 | Signed gate record for milestone M2. |

# 5. Phase 3 Tasks

Goal: one controlled write exists, with authorship taken from verified identity and with concurrency and audit behavior proven.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P3-01 | Add internal note constraints: length, content type, ticket ownership, organization. | WS-D | M | P2-18 | Database checks reject invalid notes independently of the API. |
| P3-02 | Add insert policies for internal notes for the API role only. | WS-D | M | P3-01 | Worker and auditor roles cannot insert notes. |
| P3-03 | Build add_internal_note with a strict schema and server-derived author identity. | WS-E | M | P3-02 | An author field supplied by the model is ignored or rejected. |
| P3-04 | Add OPA rules and tests for note.create, including role and ticket-state conditions. | WS-C | M | P3-03 | Policy tests cover allow, deny, and wrong-state cases. |
| P3-05 | Add expected-current-state checks to prevent stale writes. | WS-E | M | P3-03 | A concurrent modification test produces a controlled conflict, not a lost update. |
| P3-06 | Write business state and audit evidence in one transaction. | WS-E | M | P3-05 | A forced audit failure rolls back the note. |
| P3-07 | Add negative tests: cross-tenant ticket, unauthorized role, oversized content, injected instructions in note text. | WS-H | M | P3-06 | All negative cases fail safely with stable error codes. |
| P3-08 | Register the write operation in the OpenAPI document and Onyx agent. | WS-F | S | P3-06 | Only the approved write operation is callable. |
| P3-09 | Run the phase 3 test set and store results. | WS-H | S | P3-07, P3-08 | Results stored with the gate record. |
| P3-10 | Run the phase 3 gate review. | WS-E | S | P3-09 | Signed gate record for milestone M3. |

# 6. Phase 4 Tasks

Goal: a refund can be proposed, independently approved, and executed exactly once, with evidence at every state transition.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P4-01 | Create action_requests, approval_decisions, action_jobs, action_executions, idempotency tables. | WS-D | L | P3-10 | Migration applied with unique constraints on idempotency keys. |
| P4-02 | Add RLS and role grants so the worker role cannot read broad customer data. | WS-D | M | P4-01 | Worker role tests show access only to job and execution data. |
| P4-03 | Implement the action state machine with allowed transitions and transition guards. | WS-G | L | P4-01 | Illegal transitions are rejected by code and by database constraint. |
| P4-04 | Compute and store an immutable payload hash at proposal time. | WS-G | M | P4-03 | Any payload change produces a different hash and invalidates approval. |
| P4-05 | Build propose_refund with order, amount, currency, reason validation and business limits. | WS-E | L | P4-04 | Out-of-range amounts and wrong currencies are rejected before storage. |
| P4-06 | Build get_action_status returning only permitted state fields. | WS-E | M | P4-03 | Status is visible to the requester and to authorized roles only. |
| P4-07 | Add OPA rules for refund.propose and refund.approve, including limits and separation of duty. | WS-C | L | P4-05 | Self-approval is denied by policy, not only by the user interface. |
| P4-08 | Build the approval portal view showing the exact immutable payload and risk details. | WS-G | L | P4-05 | Displayed payload matches the stored hash. |
| P4-09 | Re-check approver authorization at decision time with a current token. | WS-G | M | P4-08 | A revoked approver cannot approve with an older session. |
| P4-10 | Record approval, rejection, comment, policy version, timestamp, and expiry. | WS-G | M | P4-09 | Decision rows are complete and immutable. |
| P4-11 | Build the action coordinator that queues only valid unexpired approvals. | WS-G | M | P4-10 | An expired approval never reaches the queue. |
| P4-12 | Build the worker job claim with an atomic lease and no double claim. | WS-G | L | P4-11 | Two concurrent workers claim different jobs; the same job executes once. |
| P4-13 | Verify approval state, expiry, payload hash, and idempotency reservation before execution. | WS-G | M | P4-12 | Hash mismatch, expiry, and rejection all block execution. |
| P4-14 | Build the refund provider adapter with destination, method, and operation allowlists. | WS-G | L | P4-13 | Any non-allowlisted destination is refused by the adapter. |
| P4-15 | Implement bounded retries with provider state checks for ambiguous timeouts. | WS-G | M | P4-14 | A timeout after possible success triggers reconciliation, not a blind retry. |
| P4-16 | Store outcome evidence, provider reference, and complete or release the job transactionally. | WS-G | M | P4-15 | No job remains in EXECUTING after a crash test. |
| P4-17 | Add audit events for propose, approve, reject, queue, execute, succeed, and fail. | WS-G | M | P4-16 | Full action history reconstructs requester, approver, executor, and outcome. |
| P4-18 | Register propose_refund and get_action_status in the OpenAPI document and Onyx agent. | WS-F | M | P4-06 | The model can propose but cannot approve or execute. |
| P4-19 | Build the fake provider and connect the sandbox provider where available. | WS-G | M | P4-14 | Both adapters pass the same contract tests. |
| P4-20 | Run test cases T-009 to T-013 plus concurrency and crash-recovery tests. | WS-H | L | P4-17, P4-19 | All cases pass with stored evidence. |
| P4-21 | Write the reconciliation procedure for ambiguous or failed executions. | WS-I | M | P4-16 | Runbook committed and tested against the sandbox. |
| P4-22 | Run the phase 4 gate review. | WS-G | S | P4-20, P4-21 | Signed gate record for milestone M4. |

# 7. Phase 5 Tasks

Goal: the system can be operated, observed, recovered, and released under change control.

| ID | Task | WS | Size | Depends on | Closing evidence |
| --- | --- | --- | --- | --- | --- |
| P5-01 | Select the production secret manager and move every secret out of file mounts. | WS-I | L | P4-22 | No long-lived secret in images or compose files. |
| P5-02 | Adopt workload identity for API and worker where the platform supports it. | WS-I | M | P5-01 | Services obtain credentials without a stored password. |
| P5-03 | Configure centralized logs with redaction rules and retention. | WS-I | M | P4-22 | Sampled logs contain no secret and no excessive personal data. |
| P5-04 | Configure metrics and traces across Onyx, API, OPA, database, and worker. | WS-I | L | P5-03 | One request is traceable end to end in the tooling. |
| P5-05 | Create the alerts listed in SP-OPS-001 section 7 with thresholds and owners. | WS-I | M | P5-04 | Each alert fires in a controlled test and reaches the on-call owner. |
| P5-06 | Build dashboards for authentication failures, denials, tool volume, worker retries, cost. | WS-I | M | P5-04 | Dashboards reviewed and linked from the runbooks. |
| P5-07 | Configure encrypted backups for business, action, approval, and audit state. | WS-I | M | P4-22 | Backup schedule meets the approved recovery objectives. |
| P5-08 | Perform a restore into an isolated environment and verify roles, grants, RLS, and action states. | WS-I | L | P5-07 | Restore report shows no approved job executing unexpectedly after restore. |
| P5-09 | Write the runbooks for cross-tenant exposure, injection-driven action, and credential exposure. | WS-I | M | P4-22 | Runbooks rehearsed at least once. |
| P5-10 | Add dependency, secret, source, image, and infrastructure scans to the pipeline. | WS-I | M | P4-22 | A seeded vulnerable dependency fails the pipeline. |
| P5-11 | Build immutable versioned images with provenance and a dependency inventory. | WS-I | M | P5-10 | Every deployment references an image digest, not a tag. |
| P5-12 | Stand up the isolated test environment and run the full authorization and action suites there. | WS-H | L | P5-11 | Suite results stored per environment. |
| P5-13 | Run the application, API, agent, authorization, and infrastructure security assessments. | WS-H | L | P5-12 | Findings triaged with owners and dates. |
| P5-14 | Run load, failure, recovery, and rollback tests including OPA and database outage behavior. | WS-I | L | P5-12 | Failure behavior matches SP-ARCH-001 section 10 exactly. |
| P5-15 | Complete the change-management records for prompts, tools, policy, schema, images, secrets, adapters. | WS-I | M | P5-13 | Every change type has a reviewed record. |
| P5-16 | Assemble the release evidence package from SP-OPS-001 section 11. | WS-I | M | P5-14, P5-15 | Package complete with owners, limitations, and rollback procedure. |
| P5-17 | Run the launch gate review against SP-PLAN-005 section 4. | WS-I | S | P5-16 | Signed launch decision for milestone M6. |

# 8. Cross-Phase Standing Tasks

These tasks never close. They are scheduled in every phase and reviewed at every gate.

| ID | Standing task | WS | Cadence |
| --- | --- | --- | --- |
| ST-01 | Update the threat model when a tool, destination, role, or data flow changes. | WS-H | Per change |
| ST-02 | Review every new or changed tool schema for minimum required parameters and fields. | WS-H | Weekly |
| ST-03 | Run the agent abuse and injection suite against the current tool surface. | WS-H | Per phase and per tool change |
| ST-04 | Confirm runtime database roles still hold no ownership and no bypass privilege. | WS-D | Per migration |
| ST-05 | Confirm no secret appears in source, images, prompts, logs, or model context. | WS-I | Weekly |
| ST-06 | Review OPA default-deny behavior and reason-code stability. | WS-C | Per policy change |
| ST-07 | Update decision records for accepted architectural or security decisions. | WS-H | Per decision |
| ST-08 | Review open decisions and risks in SP-PLAN-005. | WS-I | Monthly |

# 9. Definition of Ready

The task states one business or security outcome, not an implementation preference.

Its dependencies are closed or explicitly waived by the workstream owner.

Its authorization effect is understood: which subject, action, resource, and policy rule are involved.

Its test cases exist, including at least one negative and one cross-tenant case where data is touched.

It does not require a new authority for the model, a runtime service, or a database role.

Any required open decision in SP-PLAN-005 is answered.

# 10. Definition of Done

This repeats SP-BUILD-001 section 12 and is the acceptance rule for every task in this backlog.

The feature has a written business purpose and a named owner.

The tool schema exposes only required parameters and response fields.

Positive, negative, cross-tenant, and malformed-input tests pass.

Policy, database grants, and RLS behavior are tested where applicable.

Sensitive actions include approval, payload integrity, idempotency, and audit evidence.

Secrets and privileged credentials are absent from source, images, prompts, and logs.

Monitoring and controlled error behavior exist.

Documentation and the threat model are updated.