SUPPORTPILOT

Risk, Decision, and Gate Register

Open decisions, risk register, accepted conditions, and launch gate tracking

| Document ID | SP-PLAN-005 |
| --- | --- |
| Status | Live register; updated at every phase gate |
| Version | 1.0 |
| Date | 2026-09-07 |
| Parent document | SP-PLAN-001 Master Action Plan |
| Review cadence | Every phase gate and monthly |

# Purpose

This document tracks what can stop or delay SupportPilot: open decisions that must be answered, risks that must be managed, conditions accepted at a gate, and the launch gate status. It is the single register reviewed at every phase gate and monthly by the delivery team.

# Contents

How This Register Works

Open Decisions

Risk Register

Launch Gate Tracker

Accepted Conditions

Assumption Register

Prohibited Shortcuts

Register Maintenance

# 1. How This Register Works

Four lists are kept here. Open decisions are questions that only a named owner can answer. Risks are events that may happen and have an owner and a mitigation. Accepted conditions are known gaps that a gate allowed to pass, always with an owner and an expiry date. The launch gate tracker records readiness against SP-OPS-001 section 12.

Register rule: An item is never closed by time passing. It is closed by a decision, by evidence, or by a recorded acceptance with an owner and an expiry date.

| Field | Meaning |
| --- | --- |
| Status | Open, Decided, Mitigated, Accepted, or Closed. |
| Owner | The single person accountable. A role name here is itself an open item. |
| Needed by | The phase that cannot complete while the item is open. |
| Default | What happens if no decision is made. A default is never a silent weakening of a control. |
| Evidence | Where the proof lives: gate record, test result, decision record, or runbook. |

# 2. Open Decisions

These come from SP-PRD-001 section 9 and from the planning work in SP-PLAN-001. Each one blocks a specific phase.

| ID | Decision required | Owner | Needed by | Default if not decided | Status |
| --- | --- | --- | --- | --- | --- |
| OD-01 | System of record: keep local PostgreSQL as production storage, or integrate the existing support system through adapters. | Product owner | Phase 5 | Continue with local PostgreSQL and treat production migration as an open launch condition. | Open |
| OD-02 | Financial integration: which payment or order-management provider and which sandbox the refund adapter targets. | Product owner with Finance | Phase 4 | Phase 4 completes against the fake adapter only; provider evidence becomes a launch-gate condition. | Open |
| OD-03 | Tenant model: single database with organization identifiers and RLS, or physical separation for some customers. | Security lead with Product owner | Phase 5 | Keep the single-database model and record the regulatory review as outstanding. | Open |
| OD-04 | Deployment platform and managed services for production. | Operations lead | Phase 5 | Phase 5 hardening targets Docker Compose, which is not accepted for production launch. | Open |
| OD-05 | Availability targets and service-level objectives. | Product owner with Operations | Phase 5 | No objectives means no meaningful alert thresholds; monitoring work stays generic. | Open |
| OD-06 | Data retention periods for audit and business records. | Legal with Product owner | Phase 5 | Retention stays configurable but unapproved, which blocks the governance gate row. | Open |
| OD-07 | Refund approval limits per role and the exact separation-of-duty rule. | Finance with Security lead | Phase 4 | Policy uses the most restrictive interpretation: always an independent approver and the lowest configured limit. | Open |
| OD-08 | Whether prompts and full model conversations are stored, and under which purpose, access policy, retention, and redaction rules. | Security lead with Legal | Phase 2 | Conversations are not stored as audit evidence; only structured audit events are kept. | Open |
| OD-09 | Named owners for every workstream in SP-PLAN-001 section 7. | Engineering lead | Phase 0 | The plan cannot be baselined; role names remain unassigned and gates lack accountable owners. | Open |
| OD-10 | Multi-factor policy and account lifecycle for production identities. | Identity engineer with Security lead | Phase 5 | The local MFA policy is carried forward untested against production requirements. | Open |

# 3. Risk Register

Likelihood and impact use a three-level scale: low, medium, high. Exposure is the combination that drives review priority. Every risk names the signal that tells the team it is materializing.

| ID | Risk | Likelihood | Impact | Mitigation | Early signal | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Onyx to Keycloak individual OAuth forwarding takes longer than planned and blocks the critical path. | High | High | Start P1-04 in week 3 in parallel with token verification; keep a documented fallback test harness that calls the API directly with a user token. | No user-bound token reaching the API by the end of week 4. | Identity engineer |
| R-02 | Row-level security is added after application queries exist, and a table ends up owned by a runtime role. | Medium | High | Create roles and ownership in the first migration; run TS-3 on every migration. | A migration that creates a table without an explicit owner. | Database engineer |
| R-03 | Field minimization is skipped under delivery pressure and responses expose more than the approved subset. | Medium | Medium | Bounded response schemas in the OpenAPI document; obligation handling tested in TS-2 and TS-5. | A response schema containing an open object or an unbounded array. | Backend engineer |
| R-04 | Agent abuse testing slips to phase 5 and injection defects are found late. | Medium | High | TS-7 becomes mandatory in phase 2 and runs on every tool change; the corpus is versioned in P2-13. | A new tool registered in Onyx without new abuse cases. | Security engineer |
| R-05 | Approval and worker work is compressed because it starts in week 11. | Medium | High | Design the action state machine during phase 3; keep P4-01 to P4-04 as the first tasks of phase 4. | Phase 3 finishing later than week 10. | Engineering lead |
| R-06 | The provider sandbox is unavailable or its behavior differs from production. | Medium | Medium | Build the fake adapter and the sandbox adapter against one contract test set; reconcile state rather than retry blindly. | Sandbox access still unconfirmed at the start of phase 4. | Backend engineer |
| R-07 | Duplicate financial effect through retry after an ambiguous timeout. | Low | High | Idempotency key with a unique constraint, atomic claim, provider state check before retry, and TS8-09 and TS8-10. | Any retry path that does not first query provider state. | Backend engineer |
| R-08 | A secret reaches a log, a prompt, an image, or model context. | Low | High | Per-service secret mounts, redaction rules, secret scanning in the pipeline, and standing task ST-05. | A scan finding, or a log line containing a credential-shaped string. | Operations engineer |
| R-09 | OPA becomes a single point of failure and pressure grows for a local allow fallback. | Low | High | Deny on unavailable is baseline; run OPA close to the API and monitor latency; never add a fallback allow path. | Any proposal or code review comment suggesting a cached allow. | Security lead |
| R-10 | Cost or token abuse through an agent loop. | Medium | Medium | Per-session tool, time, token, and cost budgets; alerts on tool volume and model spend. | Rising tool-call volume per session in the dashboard. | Onyx owner |
| R-11 | Open decisions OD-01 to OD-04 remain unanswered into phase 5 and the launch gate cannot close. | High | Medium | Monthly register review; each decision has a named owner and a needed-by phase; escalate at the phase 3 gate. | Any decision still Open at the phase 4 gate. | Product owner |
| R-12 | Year-end holidays and the change freeze in weeks 16 and 17 compress phase 5. | High | Medium | Schedule M5 evidence preparation before the freeze and the review after it; do not plan migrations or policy publication inside the freeze. | Phase 5 tasks still open entering week 15. | Engineering lead |
| R-13 | A support user with several roles approves an action they requested. | Low | High | Separation of duty enforced in policy, not only in the portal; TS8-03 runs in every phase 4 change. | Any policy change that removes the requester check. | Security lead |
| R-14 | Restored backups reactivate old approved jobs. | Low | High | Restore procedure verifies action states and neutralizes stale approvals; TS9-08 proves it. | A restore drill that does not inspect action state. | Operations engineer |
| R-15 | Test data drifts from the fixed baseline and negative tests silently stop being negative. | Medium | Medium | Seed script is the only source of test data; SP-PLAN-003 section 2 names are fixed and referenced by the suites. | A test that creates its own organization or user inline. | Security engineer |

# 4. Launch Gate Tracker

Rows come from SP-OPS-001 section 12. Status starts as Not started and moves to Ready only when the evidence named in SP-PLAN-004 exists. The launch decision at milestone M6 reads this table.

| Gate | Pass condition | Evidence source | Status |
| --- | --- | --- | --- |
| Product | Approved scope, owners, roles, user journeys, and prohibited actions. | SP-PRD-001 plus OD-09 closure. | Not started |
| Architecture | Documented data flow, trust boundaries, control-plane separation, and network rules. | SP-ARCH-001 plus phase 0 network evidence (V-02). | Not started |
| Identity | Individual authentication, MFA policy, token checks, and service identities tested. | TS-1 results plus OD-10 closure. | Not started |
| Authorization | OPA default deny and the full role and resource matrix pass. | TS-2 and TS-6 results with policy version. | Not started |
| Database | Least-privilege roles, RLS, backups, restoration, and migration controls pass. | TS-3, TS-4, and TS9-07 results with schema version. | Not started |
| Agent | Narrow tools, strict schemas, loop limits, and injection tests pass. | TS-7 results plus the registered operation list. | Not started |
| Actions | Approval integrity, separation of duties, idempotency, reconciliation, and audit pass. | TS-8 results plus the reconciliation runbook from P4-21. | Not started |
| Operations | Dashboards, alerts, runbooks, on-call ownership, rollback, and incident process ready. | TS-9 results plus P5-05, P5-06, and P5-09 deliverables. | Not started |
| Security assessment | Material confirmed issues are fixed or formally accepted with owners and dates. | P5-13 findings list and section 5 of this register. | Not started |

# 5. Accepted Conditions

A conditional gate pass creates a row here. An empty table is the correct state at the start of the project. No row may exist without an owner and an expiry date.

| ID | Condition accepted | Gate | Owner | Expiry | Removal evidence |
| --- | --- | --- | --- | --- | --- |
| AC-01 | (none recorded at version 1.0) | - | - | - | - |

Acceptance limit: An S1 defect from SP-PLAN-004 section 10 can never become an accepted condition. Cross-tenant exposure, execution without approval, duplicate financial effect, and credential exposure are fixed before a gate passes.

# 6. Assumption Register

Assumptions AP-01 to AP-08 in SP-PLAN-001 section 2 are tracked here once they are confirmed or broken.

| ID | Assumption | Confirm by | Status | Action if broken |
| --- | --- | --- | --- | --- |
| AP-01 | Week 1 begins 2026-09-07 with five-day weeks. | Phase 0 gate | Assumed | Rebaseline every milestone date in SP-PLAN-001 section 5. |
| AP-02 | One delivery team with the listed roles. | Phase 0 gate | Assumed | Extend phases 2 and 4 first; do not shorten security phases. |
| AP-03 | Local Docker Compose is sufficient for phases 0 to 4. | Phase 1 gate | Assumed | Move the affected phase to the integration environment and extend phase 0. |
| AP-04 | Model provider access is available in week 1. | Phase 0 gate | Assumed | Phase 1 read flow is proven through the direct API harness until access exists. |
| AP-05 | Refund execution uses a sandbox, never a live financial system. | Phase 4 gate | Assumed | Stop phase 4 execution work and escalate to the security lead and product owner. |
| AP-06 | A security reviewer is available for every gate. | Phase 1 gate | Assumed | Gates queue; the launch date moves rather than a gate being skipped. |
| AP-07 | Open decisions are answered by their needed-by phase. | Monthly review | Assumed | Apply the recorded default or stop the dependent workstream. |
| AP-08 | No gate falls inside the week 16 to 17 change freeze. | Phase 4 gate | Assumed | Move M5 and M6 later; do not publish policy or run migrations during the freeze. |

# 7. Prohibited Shortcuts

These appear whenever a schedule is under pressure. Each one invalidates the security baseline and every test result produced after it. None of them may be accepted as a condition at any gate.

| Shortcut | Why it is refused |
| --- | --- |
| Disable row-level security or grant BYPASSRLS to make a query work. | It removes the second authorization layer that protects against application mistakes. |
| Let the API own protected tables to simplify migrations. | Table owners normally bypass row policies, so tenant isolation stops being enforced. |
| Add a cached allow path when OPA is unavailable. | Deny on unavailable is baseline; a fallback allow converts an outage into an authorization bypass. |
| Accept organization or user identifiers from tool arguments. | Model arguments are untrusted input; identity comes only from the verified token and server records. |
| Register a generic SQL, shell, or HTTP tool for convenience. | It gives the agent authority that cannot be tested or bounded. |
| Allow the API to execute a refund directly to avoid building the worker. | It removes the separation between request, approval, and execution. |
| Let a requester approve their own action in a test tenant and keep the code path. | Separation of duty must be enforced in policy, not in the interface. |
| Mount the migration credential into a runtime service. | A runtime compromise would then grant schema, grant, and policy administration. |
| Skip audit writes to improve latency. | A sensitive state change without evidence cannot be reconstructed or defended. |

# 8. Register Maintenance

The engineering lead reviews every open decision and risk at each phase gate and records changes in this document with a new version number.

The security lead reviews accepted conditions monthly and escalates any item within two weeks of expiry.

A new risk is added with a likelihood, an impact, a mitigation, an early signal, and an owner, or it is not added at all.

A closed item keeps its identifier and its evidence reference; identifiers are never reused.

The launch gate tracker is updated only from stored evidence, never from a verbal report.